## Slide 1: AI Innovation Companion - Doraoumon
Create an efficient tool to significantly accelerate the conversion process from innovative ideas to project charters and enhance the structural quality and decision-making effectiveness of innovation project proposals.
300K Euro
Build an AI-driven innovation empowerment application that cover the entire process, from guiding users to define business pain points, to intelligently generating technical solutions, and finally to automatically creating a project charter.
Reduce the average time from initial idea to a complete project charter by 50% compared to traditional manual methods 80% of project charters generated by the system are rated as 'Executable' or 'Highly Executable' by internal end users, e.g. project managers
Generate at least 50 complete project charters within 3 months of launch.
Total: 30K Euro
ANS, SAM, AM, UX, Central Function
Complete product design and technology selection. Deliverables include a UX prototype with the full interaction flow and a finalized technical architecture. (Weeks 1-2)
Complete MVP development of core features. Implement the core workflow from pain point input to technical path generation, and complete initial prompt engineering. (Weeks 3-6)
Complete the project charter auto-generation and optimization features. Achieve the full 'Why-How-Charter' closed loop with backend data management system. (Weeks 7-10)
Official product launch and promotion. Complete all feature optimizations, documentation, and roll out to the first batch of users. (Weeks 11-12)
Details: Labor Cost (labor): 30K Euro
Equipment & Material (material): NA 3rd Party Supplier (3rd-party): NA
17th Jan. to 16th Apr. 2026
Notes: Within 6 months of launch, the system is adopted by at least 2 internal business departments or reach 100 users for their innovation process management